## Sheet1
question_text | option_1 | option_2 | option_3 | option_4 | explanation | answer
You are a project manager of a company and your project is currently in execution phase. The customer has requested you for additional work. This work will affect the budget but not the schedule of the project. What should you do next? | Add the additional requirements to the project plan | Ignore the request | Explain the change procedure and ask to submit a request for change | Discuss with the project team about the change | No Expl | 3
Your company policy allow to gift exchange with customer within certain limit. By mistake, you have given a gift to the customer's representative already which is beyond the limit mentioned in your company policy. What should you do? | Forget it and don't tell to anyone. | Contact your company's senior management and ask for assistance | Ask your customer to return the gift | Ask your customer to gift you which cost same | No Expl | 2
You are working with an organization and you found that one stakeholder not disclosing all of the costs involved with an upcoming project. Rather, this PMP is constructing a WBS that does not include all the tasks necessary to get the project done. What should you do? | Talk to the PMP about the WBS to see if you can rework it to reflect actual costs of the project | Confront the other project manager immediately | Mail to PMI headquarters | Ignore it | No Expl | 1